## I-Use
No | Title | Sub-item | Criticality | Description | Pain Point | System | Target | Document readiness | Change Committee sitting | Status | User demo | Deployment | Comm. | Remarks | Comment GIT | Assessment
1 | BE-TM Force improvement based on TDI Pilot findings | (a) Gated CU within 3 days | No | System will be able to remind user to not close CTT CU within 3 days and able to avoid CTT repeat report and improve customer experience. | CTT able to close < 3days for CU that impact repeated CTT. | TM Force | To get update from GIT | 13th July | 12th August | Assessment |  |  |  | Require date to deploy as not included in 1( e) / not in the list. [26/05]GIT to assess |  |  | to reply email 19th oct
|  | (b) Appointment slotting 1 hour after CTT created | Yes | Appointment slotting visible 1 hour after CTT activity created. | FL able to slot upfront appointment within the slimmest gap time cause SDZ do not have enough for time travelling. | TM Force | 1(d) | 13th July | 12th August | Assessment | 1e2a | 1e2a | 1e2a | Pending request from UAT: (i) System shall blur the date and slot time (ii) Total counter should exclude previous time (iii) RCC able to slot immediately | *(3)
|  | (c ) Assistance assignment acceptance activity | No | 1. bypass unnecessary step in updating status for “assistance assignment” activity and 2. to be notified (pop-up notification) if there is a request on this activity 3. Assistance assignment activity (configurable) | SDZ to update unnecessary status for “assistance assignment” activity. | TM Force | 1 (c ) | 13th July | 12th August | Closed | 10th August | 10th August | 10th August | Has been deploy and configurable
|  | (d) Enable appointment slotting directly from reschedule status | No | Able to book appointment directly from Reschedule activity status; without change status to Pending Assign. | RCC has to change Activity to Pending Assign before able to reschedule for book appointment slot. | TM Force | Pending update from GIT | 13th July | 12th August | Closed | 1e2a | 1e2a | 1e2a | Require date to deploy as not included in 1( e) / not in the list.
|  | (e) Appointment slotting during weekend | No | Able to book appointment base on SDZ daily session availability (Monday-Sunday) and will be reflected correctly at appointment slotting and FL. | AM/PM appointment slotting limitation and building management closed during weekend; 1) upfront appointment has been offered to customer on evening session while FT is only working half day-morning. 2) upfront appointment has been offered to customer although building | TM Force | 1( e) | 13th July | 12th August | Closed | 1e2a | 1e2a | 1e2a | Require date to deploy in 1( e) as critical item. | (6) Comment from GIT: Propose to manage in Leave Management until post nationwide rollout. Will have a special drop in Q1 2021. | 1.To allow team to apply for work by AM / PM during weekend and Public Holidays 2.Slotting will be based on leave and work mgmt. and percentage configured in portal.
|  | (f) Proactive CTT/Activity monitoring from RCC view | No | Sufficient info in CTT list and Activity list for proactively monitoring. | Difficulties to monitor active CTT/Activity. | TM Force | 1( e) | 13th July | 12th August | Closed | 1e2a | 1e2a | 1e2a |  | *(10) | Activity list: 1.To have search by status. 2.Can be search by multiple status LOVs. 3.Include Customer Name Ticket list: 1.To have search by status. 2.Can be search by multiple status LOVs. Activity history: 1.Add CTT number, Cause Code, Cause Category, 2.Closed Date time at Activity history at RCC monitoring
|  | (g) Enable activity assignment without CTT | No | Enable activity without CTT | SDZ Executives/Supervisor/RCC unable to track SDZ overall task. Current productivity only counted based on CTT completed by SDZ. | TM Force | 1(d) | 13th July | 12th August | Closed | 1e2a | 1e2a | 1e2a
|  | (i) Trigger service number for phone dialer | No | Able to make a phone call from all customer phone number available in tablet (service number/primary/secondary/CTT contact). | In current design only contact number field can be used by SDZ to call customer. If this number unreachable, SDZ unable to call using customer service number although it is available in tablet. SDZ has to remember service number and make a call from another device. | TM Force | 1( e) | 13th July | 12th August | Closed | 1e | 1e | 1e |  | *(16) | It is advised to use SERVICE_NO instead of N_SERVICE_ID, because N_SERVICE_ID may consist mixed of alphanumeric which not relevant for dialing
|  | (j) GIS tracker to display CTT open(active) only | No | GIS tracker to display/monitor the actual CTT in-hand and locations in a single view on that day. | SDZ Executives/Supervisor unable to monitor actual unresolved activities in-hand in GIS tracker due to: 1. Ticket tab: Unnecessary CTT - display all CTT not according team and historical CTT 2. Team tab: Mixed activity (history and current) information display in tracker. | TM Force | 1( e) - Phase 2 | 13th July | 12th August | Closed | 1e2a | 1e2a | 1e2a |  | *(12) | 1.Display all activities on that day (all status). 2.Selection on team tab should be reflected in ticket tab.
|  | (k) Expand short pop-up list | No | Full display pop-up list. | Short list view cause SDZ to choose the wrong LOV | TM Force | 1( e) | 13th July | 12th August | Closed | 1e2a | 1e2a | 1e2a |  | *(17)
|  | (l) Enable CTT/Activity history (activity complete) from tablet | No | As a user (SDZ), I want able to search CTT/Activity history directly from tablet. Business Rules Data range: 1 month. System to display CTT details. | SDZ unable to search CTT/Activity history directly from tablet. | TM Force | 1( e) | 13th July | 12th August | Closed | 1e2a | 1e2a | 1e2a |  | *(18)Comment GIT: System will only display summary of task | System will only display summary of task
|  | (m) Display 3 customer contact numbers | Yes | To display at least 3 customer contact number | CTT long restoration due to CU, RCC dependencies to only 1 contact number | TM Force |  |  |  | To follow up |  |  |  | [26/05]Deliver in CASE |  |  | deliver kat case
2 | Bypass secure VPN | Bypass secure VPN | No | Bypass the secure-vpn in order to allow TM Force Portal and SPANMS in TMForce to be accessed from public network | In current situation, users need to access TM Force Portal and SPANMS in TMForce Tablet via secure-vpn. | TM Force |  | 13th July |  | Closed |  |  |  | Item closed due to GIS not approve | Item closed due to GIS not approve | Item closed due to GIS not approve
3 | Enabling R&R TM Point ID for CSL Upfront Appointment | Enabling R&R TM Point ID for CSL Upfront Appointment | No | Enhancement of enabling “SWIFT tab” for TM Point agents is needed in order to visible CSL upfront appointment. | In current situation, TM Point unable to perform upfront appointment due to ID limitations. | TM Force | 20th July | 15th July |  | Closed | 20th July | 20th July | 20th July | Item Completed | Item Completed | Item Completed
4 | Integration SPANMS and Camelia | Integration SPANMS and Camelia | No | Enhancements to allow SPANMS and Camelia able seamless access from TMForce tablet. 1) to have spanms web view in tmforce mobile 2) to have service and dp line test capability to camelia 3) to capture history reading from ideas on session status, physical reading & camelia output - remarks + point of failure | In current situation, users need to access SPANMS and Camelia in TMForce Tablet via secure-vpn. | TM Force | 1( e) | 4th August |  | Closed |  |  |  | Refer 8(b)
5 | BE-GIS tracker and Main dashboard | (a) Main dashboard | Yes | Sufficient info in CTT list and Activity list for proactively monitoring. | Difficulties to monitor active CTT/Activity. | TM Force | 2021-03-01 | 17th August |  | Assessment |  |  |  | Emailed to GNT PIC for consolidation [26/05]GIT to assess | Emailed to GNT PIC for consolidation | Emailed to GNT PIC for consolidation
|  | (b) GIS tracker | Yes | GIS tracker to display/monitor the actual CTT in-hand and locations in a single view on that day. | SDZ Executives/Supervisor unable to monitor actual unresolved activities in-hand in GIS tracker. | TM Force | 2021-03-01 | 17th August |  | Assessment |  |  |  | Emailed to GNT PIC for consolidation [26/05]GIT to assess | Emailed to GNT PIC for consolidation | Emailed to GNT PIC for consolidation
6 | Effective activity service(SDZ) escalation to network(ENZ) | Effective activity service(SDZ) escalation to network(ENZ) | No | Enabling multiple option of escalation case from SDZ to ENZ with: a) 2nd level; (will be routed to Manual Task) b) Proceed with NTT; (NTT will be auto created) c) ENZ further checking; (proceed as per current Investigation Activity) | In current situation, there is only one option escalation from SDZ to ENZ (via Investigation Activity) | Camelia | Pending update from GIT | 17th July |  | Assessment
7 | NTT Gated | NTT Gated | No | NTT Gated: Auto bulk CTT (Mass Market) status change to ‘Closed’ upon NTT ‘Resolved’ triggered by gated, with verification checklist available and session verification and auto closed NTT once all CTT(Mass Market) closed with symptom code fault; CTT(Mass Market) pending verify with symptom code performance while CTT(MA & GW) in pending verify status. | In NOVA environment where CTT is created and linked to NTT, CTTs were not auto-closed after NTT Resolved and TMUC/RCC has to manually verify; while in ICP environment a) for NTT Active element - CTT auto-bulked closed without service-gated and manual network-gated; b) for NTT Passive element – CTT auto-bulked closed with gated | Camelia | Pending update from GIT | 17th July |  | Assessment
8 | Learnings from Assurance Pilot and improvements/enhancement prioritization for Phase 1e | (a) VVIP and urgent case | No | As a user (TL/RCC), I want to have a visibility for buffer appointment slot. So that, I’m able to slot appointment to any VVIP or urgent case customer. As a user (TL), I want to be able to escalate VVIP or any urgent case to RCC for the case of buffer appointment slotting full. So that, customer will be able to have appointment slot base on preferred time and RCC able to take action immediately. Business Rules 1. Alert notifications to RCC once escalated from TL 2. No KCI to customer until appointment been confirmed | FL unable to offer upfront appointment to VVIP or any urgent case to customer for the case of appointment slotting full. Workaround solution: FL send email to RCC. RCC manual assign to SDZ (if available). | TM Force | 1( e) | 28th August 2020 |  | Closed |  |  |  |  | *(4) | 1.For urgent cases, CC to input urgent date at remarks /notes column. 2.RCC/Team leader able to view 100% slot available for same day slot only. 3.RCC to manual assign to team
|  | (b) SPANMS, CAMELIA & IDEAS in mobile - info during CTT create & fault verification | No | Enhancements to allow SPANMS and Camelia able seamless access from TMForce tablet. 1) to have spanms web view in tmforce mobile 2) to have service and dp line test capability to camelia 3) to capture history reading from ideas on session status, physical reading & camelia output - remarks + point of failure | In current situation, users need to access SPANMS and Camelia in TMForce Tablet via secure-vpn. | TM Force | 2021-01-01 | 28th August 2020 |  | Drop |  |  |  |  | *(13) | 1.To have 2 new tabs in activity detail in mobile : a.SPANMS – to have integration with SPANMS to display info below from SPANMS i.Dashboard ii.Access Network iii.Speedtest iv.IEMT v.Voice Status vi.IPTV b.Camellia – to have integration with camellia to display real time service and DP line test for both unifi and preunifi
|  | `(c) Gated to auto closed | No | Auto qualifier checking from system. To configure gated activity based on dedicated service affected and specific LOV. | Current gated unable to differentiate activities base on single service affected. In TM Force gated is disable and SDZ has to manually check service quality before able to proceed with CTT closed that might impact First Fix Right performance. | TM Force | 2021-03-01 | 28th August 2020 |  | Assessment |  |  |  | [26/05]To write up new CR. Pending RnD to share latest slide/excel matrix. | To be developed during CASE development / integration Dependency in CASE escalation process |  | drop dulu sebab tunggu case
9 | TM Force fine tuning workshop - upfront appointment | (a) Prefered appointment date algorithm | Yes | System to flexible enough after CTT resolved – pop up CTT “customer preferred time” and “at anytime” offering (i) If appointment available >1.25hrs before next appointment, system will offer slot to preferred appt (ii) If <1.25hrs system will not offer next appt | In current situation, customer prefered time slotting is manually monitor by RCC | TM Force | 2021-03-01 | 2020-09-01 |  | Assessment |  |  |  | [26/05]GIT to assess
|  | (b) Multiple CTT with the same address | Yes | (i) System suggested the same slot (ii) System slotted to the same SDZ | In current situation, customer prefered time slotting is manually monitor by RCC | TM Force | 2021-03-01 | 2020-09-01 |  | Assessment |  |  |  | [26/05]GIT to assess
|  | `(c) CTT failure & appt >6hrs from CTT creation | Yes | (i) Perform session verification after 4hrs CTT created (ii) Checking by radius system (iii) SMS verification from customer | 30% CTT cancel. Line up before SDZ attend the CTT | TM Force | 2021-03-01 | 2020-09-01 |  | Assessment |  |  |  | [26/05]GIT to assess
|  | (d) Customer tagging at anytime | Yes | FL to slotting: (i) Cust preferred time or (ii) At anytime | Customer to queue appointment slotting evethough customer available at anytime | TM Force | 2021-03-01 | 2020-09-01 |  | Assessment |  |  |  | [26/05]GIT to assess
|  | (e) Return LR from SDZ with link appointment | No | Common fault=NO, send SMS with link to UNIFI portal. Cust can set appointment via portal If no reply from customer within 2hrs, revert CTT(Pending Assign) to RCC for appointment setting. | LR return to SDZ without appointment | TM Force | To get update from GIT | 2020-09-01 |  | KIV | [6 empty] | to further clarify
|  | (f) Appointment forecasting | Yes | (i) CTT inflow (ii) weather |  | TM Force | 2021-03-01 | 2020-09-01 |  | Assessment |  |  |  | [26/05]GIT to assess
10 | TMFORCE Assurance Network Operation Manpower Planning Workshop - Findings | (a) Tagging TT by building - to avoid unnecessary slot on weekend - applicable to urban/sub urban area | No | As a user (FL/SDZ), I want system able to identify and block the appointment slot base on list of premises that cannot access during weekend. So that, I’m able to offer customer with valid appointment. | FL don’t have the visibility list of building inaccessible due to building maintenance unavailable during weekend. There is a possibility unnecessary CTT created and attended during weekend. | TM Force |  | 2020-09-01 |  | Assessment |  |  |  | [26/05]GIT to assess
|  | (b) Enable Team configuration/tagging by specific building - applicable to urban/sub urban area | No | As a user (RCC), I want to have upfront verification slot availability to registered HRBF. So that, CTT will directly auto-assign to the correct team and SDZ will immediately perform the restorations. | RCC has to manually re-assigned CTT that only specific team can access the building, Designated Team by Premise - HRBF - High Rise Building Fiberization (specific cabinet registered to HRBF) that will cause the delay of restorations. | TM Force |  | 2020-09-01 |  | Assessment
|  | (c) Slot configuration by building (Currently only by Zone) - applicable to rural/remote area | Yes | As a user (SDZ), I want to have slotting configurations at zone, node, skillset and cabinet level and to have flexible amount So that I will have a flexibility on travelling/slotting base on area and able to meet customer appointment time. | Current slotting configurations at Zone level may cause the problem to the combination urban, sub-urban, rural and remote area in the same zone. This may lead to unattended CTT/miss-appointment due to long travelling hours. | TM Force |  | 2020-09-01 |  | Assessment
|  | (d) Disable slot on Friday 12-1pm - applicable to all | Yes | As a user (FL), I want system to block upfront appointment at 12pm-1pm on Friday. So that, I’m able to offer customer with valid appointment. | FL able to slot upfront appointment at 12pm-1pm on Friday; while team is not available to attend the CTT due to Friday prayers. | TM Force |  | 2020-09-01 |  | Closed
|  | (e) Auto assignment to 1Man Team or 2Man Team - applicable to all | Yes | As a user (SDZ), I want to have auto qualifier checking from system for CTT 1-man/2-man team in auto-assignment algorithm. So that, I’m able to get the correct assignment and immediately perform the restorations. | Require manual intervention from RCC to swap TT between 1-man and 2-man team. | TM Force |  | 2020-09-01 |  | Assessment
11 | Dashboard | Dashboard | Yes | Dashboard |  | TM Force |  | 1st February 2021 |  | Assessment
12 | TM Force enhancements re-alignment after rollout | (a) To display OLT NE Id at activity list | No | As a user (RCC), I want system able to display OLT NE ID column at “Ticket List” and “Activity List” portal. So that, I’m able to proactively monitor CTT due to network outage and escalate to respective team. | RCC unable to monitor CTT with the same OLT NE ID to handle scenario network issue for the case of CTT leakage; cause delay in escalating the case to network team. | TM Force |  | 1st February 2021 |  | Assessment
|  | (b) Team workload able to view by RCC (per specific team) | Yes | As a user (Portal user), I want to have visibility of FT (only) Team Workload specific to filtration selection. So that, I’m able to proactively monitor activity status/progress. | Current Dashboard-Team Workload display all user tagging to the particular building id. RCC having difficulties to proactively monitor CTT progress. | TM Force |  | 1st February 2021 |  | Assessment
|  | (c) Colour code notifications/alert to RCC for manual assign | No | As a user (RCC), I want system notify by color code staff ID at "Assigned to". So that, can alert me to manual assign CTT to SDZ. | RCC unable to identify CTT that need to manual assign to SDZ for the case of system unable to find standby team cause the delay of CTT restorations. | TM Force |  | 1st February 2021 |  | Assessment
|  | (d) To exclude VOC if resolved reason = Customer request to cancel | No | As a user (CX), I want system to not send VOC to customer if RCC/SDZ select LOV: a) UNIFI: Customer_Cancel TT b) BAU: CWL during Activity Resolved/Ticket Closure. And to exclude to exclude VOC triggered during CTT linked to LR. | Currently VOC been triggered to customer if RCC/SDZ select LOV: a) UNIFI: Customer_Cancel TT b) BAU: CWL during Activity Resolved/Ticket Closure. Customer will receive the unnecessary KCI SMS that leads to low performance rating. To exclude VOC triggered during CTT linked to LR. | TM Force |  | 1st February 2021 |  | Assessment
|  | (`e) Improve portal filtration | No | As a user (RCC/Exec/SP), I want to have: a) Team Management, Ticket History, Activity History, Team Report (Asn) and Audit Log able to filter by area b) Team workload - team status (working/on leave) c) CTT history - appointment date/closed date | Difficulties to monitor/search by specific info due to not enough filtration function leads to CTT aging. | TM Force |  | 1st February 2021 |  | Assessment
|  | (f) To have new column for 1MT/2MT or "attached team" during manual assignment by RCC | No | As a user (RCC/Exec/SP), I want to have visibility of 1MT/2MT or “attached team” at Manual Assign page. So that, I’m able to identify team capacity to perform CTT restorations. | RCC has to manually check team availability/capacity for assignment activity that cause the delay of CTT restorations. | TM Force |  | 1st February 2021 |  | Assessment
|  | (g) Assignment special slotting by RCC | Yes | As a user (RCC), I want to have special appointment slotting functionalities. So that, I’m able to assign special slot to SDZ. (unlimited slotting) | RCC unable to assign CTT to SDZ for appointment slotting beyond office hour. For the case of SDZ has completed the assignment, RCC unable to assign extra CTT in the same slot to SDZ due to capping by daily appointment slotting. | TM Force |  | 1st February 2021 |  | Assessment
|  | (h) Attached-detached partner team | Yes | As a user (SDZ), I want to be able to attached-detach my partner. So that, CTT will be attended whenever TL is on leave. Business Rule: Carry CPE in-hand list. | SDZ unable to attached-detached partner from mobile. SP/support team has to manually configure in system to enable working partner whenever team leader is on leave. | TM Force |  | 1st February 2021 |  | Assessment |  |  |  | [26/05]Under testing by GIT
|  | (i) Intelligent backup team skillset | Yes | As a user (RCC/SP), I want to be able to Manual Assign activity to backup team. So that, team able to manage CTT backlog accordingly (fast track). | RCC unable to Manual Assign activity to backup team. Backup team is applicable to only specific skillset. | TM Force |  | 1st February 2021 |  | Assessment
|  | (j) CTT history enable at tablet | No | As a user (SDZ), I want to be able to have the information of CTT history for date selection of resolved date (Deliver as per in SWIFT). | Current CTT history will display a month range from date CTT search. | TM Force |  | 1st February 2021 |  | Assessment
|  | (k) TROS/SDZ subzone | No | As a user (TM), I only want to attend activity within my own cabinet; not TROS cabinet. So that, I’m able to attend CTT at correct area. | Current scenario, TROS share same subzone with TM but only attended their own cabinet. | TM Force |  | 1st February 2021 |  | Assessment
|  | (m) To include cabinet info in notifications | No | As a user (SDZ), I want to have cabinet details in notifications. So that, able to alert my next location to attend. | Current scenario, notification only display CTT number. | TM Force |  | 1st February 2021 |  | Assessment
|  | (l) Reason manual assign | Yes | As a user (RCC), I want to have reason for manual assign with dedicated LOVs. So that, report able to be generate from raw data for analysis. LOVs (configurable): a) 1-man team to 2-man team b) CTT multiple address c) Fast track | RCC has to manual compile on reason for manual assign. | TM Force |  | 1st February 2021 |  | Assessment